## Sheet1
Pharse 1: Design layout				Release feature
Date	Tasks	Working Hours		Release Date	Feature
10/08/13	Design application's template	2		10/12/13	Release design & Waiting feedback
10/09/13	Design application's template	2		10/19/13	Release application with layout (non function)
10/10/13	Design application's template	2		11/06/13	Release android app (full function)
10/11/13	Design application's template	2
10/12/13	Release design & Waiting feedback	N/A		Summary
10/13/13	Waiting feedback & Programmer learning design	N/A		Duration	Total Hours
				29 days	35 hours
Pharse 2: Build application with layout
Date	Tasks	Working Hours
10/14/13	Apply design layout to application	2
10/15/13	OFF
10/16/13	Apply design layout to application	2
10/17/13	Apply design layout to application	2
10/18/13	Apply design layout to application	2
10/19/13	Release application with layout (non function)	N/A

Pharse 3: Implement functions
Date	Tasks	Working Hours
10/20/13	Implement form inputing data	1.5
10/21/13	Implement form inputing data	1
10/22/13	OFF
10/23/13	Implement compass image depend on inputing data	2
10/24/13	Implement compass image depend on inputing data	2
10/25/13	Implement compass image depend on inputing data	1
10/26/13	OFF
10/27/13	Implement compass can work with phone's direction	1.5
10/28/13	Implement compass can work with phone's direction	1.5
10/29/13	Implement compass can work with phone's direction	2
10/30/13	OFF
10/31/13	Implement form result with dynamic dynamic data	1.5
11/01/13	Implement form result with dynamic dynamic data	1
11/02/13	OFF
11/03/13	Integration with web team to show the results	1.5
11/04/13	Integration with web team to show the results	1.5
11/05/13	Integration with web team to show the results	1
11/06/13	Release android app (full function)